## Capability Matrix
Capability | Business purpose | Requirement evidence | Implementation status (verified) | Launch criticality | Customer impact | Sentinel dependency | Remediation required | Proposed release | PO decision required
Company registration | Freight/logistics company signs up, gets tenant + portal | Core product purpose (AGENT.md) | VERIFIED — /register → plan modal → template → onboarding (P21-01..03) | Core | Cannot onboard customers without it | Tenants page: approve/suspend/launch (WORKING) | None for basic flow | Launch | —
Individual shipper registration | Personal account for individuals shipping goods | PO registration model | VERIFIED — /register personal flow, sign-in, personal dashboard | Core | Individual customers blocked otherwise | Users list (WORKING) | None | Launch | —
Staff invitation | Company owner invites employees with roles | PO registration model | VERIFIED — invite email → accept → password → workspace; roles enforced (P21-08..10) | Core | Multi-user companies blocked otherwise | Users page; team oversight | None | Launch | —
Vendor registration + marketplace | Partner/vendor onboarding, approval, bookings, dispatch | AGENT.md vendor ops; PO: challenge deferral | PARTIAL — FULL backend exists: POST /vendors/register (public, rate-limited), documents, availability, marketplace match, bookings accept/reject, admin review+suspend. NO customer/vendor-facing UI built | PO decision — is marketplace part of launch model? | Vendors cannot self-onboard via UI; API-only path | Vendor pages: list/review/suspend (WORKING) | Build vendor registration page + vendor portal/dashboard UI + tenant marketplace UI | PO decision | YES — include vendors at launch, or approve deferral?
Driver self-service (sign-in, job updates) | Drivers authenticate and update jobs | PO: conditional — needed for driver-operated workflow | MISSING — drivers exist only as managed records (Fleetbase proxy); vendor bookings carry driver_name/phone + position tracking, but no driver auth or app | PO decision — managed-record fleet mgmt may suffice initially | Drivers cannot interact with the platform | None currently | Build driver identity + mobile flow if approved | PO decision | YES — launch with managed drivers only, or require driver portal?
Shipment create/list/lifecycle/tracking | Core freight operations | Core product purpose | VERIFIED — create, status transitions, public tracking (P21-04..07, UAT tests) | Core | Platform is meaningless without it | Shipments admin list (WORKING) | None for operations | Launch | —
Shipment status notifications | Customers informed of status changes | PO: core gap — customers should receive updates | DEFECTIVE — send_shipment_status_update_email + delivered email exist and ARE wired in record_tracking_event (shipment_service.py:948-968), but the UI transition endpoint (POST /transition) bypasses that path and sends nothing; recipient is tenant contact only, not end customer; send failures swallowed to logs | Core | Customers get zero shipment updates today | None | Wire notifications into transition path + define recipient (customer vs tenant) + surface failures | Fix before launch | YES — who receives notifications (tenant owner, end customer, both)?
Public tracking | Anyone tracks shipment by reference | Core | VERIFIED — apex + tenant portal tracking (P21-07) | Core | — | Tracking page (WORKING) | None | Launch | —
Tenant-portal support tickets | Public submits tickets on a company's portal | Core | VERIFIED — submit, confirmation email, token tracking, admin list + status updates (P21-12; write path verified) | Core | — | Tickets list + status PATCH (WORKING) | None | Launch | —
Central Afruheritage platform support | Platform-level support independent of tenant tickets | PO: core gap | MISSING as ticket channel — public tickets require tenant_id (422 without); apex /support honestly explains tenant-routing. Help assistant + branded email exist as informal channels | High if PO requires central support at launch | No channel for platform-level issues (billing disputes, onboarding help) | Admin tickets view covers all tenants — intake path missing only | Add platform-scope ticket path (tenant_id optional) + apex intake form, or stand up support@ workflow | PO decision | YES — is central ticket intake required at launch?
Plan/trial subscription lifecycle | Trial activation, cancel/pause/resume, plan view | Core | VERIFIED — trial activation ~550ms, subscription lifecycle endpoints, billing page | Core | — | Billing admin: plans/promotions/wallets/subscriptions proxies (WORKING) | None for trial scope | Launch | —
Live payment collection (charges) | Real-money subscription payments | PO: commercial blocker for paid launch | IMPLEMENTED-UNVERIFIED — Paystack + Flutterwave clients exist (initialize/verify, webhooks, authorization_url flow); never exercised end-to-end with real keys in UAT | Depends on launch model — required if charging at launch | Cannot collect revenue if broken | Payments admin list (WORKING); refund/dispute MISSING | End-to-end charge test with live keys; decide refund/dispute scope | PO decision | YES — go-live with paid billing now, or trial-only launch?
CRM contacts + quotes | Manage customers and quotations | Product scope | VERIFIED — /crm, /crm/contacts, /crm/quotes pages + backend CRUD | Core if CRM sold | — | None currently | None | Launch | —
CRM activity history | Follow-up notes, calls, activity log per customer | PO: needs remediation | PARTIAL — CrmActivity model + GET/POST /customers/{id}/activities endpoints exist; no UI surface for activities | PO decision | Cannot record customer follow-ups via UI | None | Add activities UI to CRM customer detail | PO decision | YES — is CRM activity UI required at launch?
Tenant storefront (fleet/freight templates) | Published branded company portal | Core | VERIFIED — template selection, publish, live tenant storefront; fabricated vendor/stat/route content removed | Core | — | Templates page (WORKING) | None | Launch | —
Additional storefront templates (5 demos) | Mall/ecommerce/restaurant/booking/real-estate themes | Optional | PARTIAL — previewable, publish-blocked (fake-content themes now degrade to generic shell) | Low — PO: reasonable deferral | Cannot publish these themes | Templates page | Make tenant-configurable before publishing | Post-launch | Confirm deferral
Custom domains | Customer-owned domain for portal | Domain policy: subdomain first | PARTIAL — custom_domain_events + domains admin exist; end-to-end custom-domain flow unverified | Low for launch | Subdomain works as recovery route | Domains page (WORKING) | Verify or defer | Post-launch | Confirm deferral
Warehouse operations | Warehouse management module | Unclear if in product scope | MISSING — no implementation found; not in customer nav | PO: depends on product scope — works or remove from offering | — | None | Implement, or explicitly remove from offering/docs | PO decision | YES — does Afruheritage sell warehouse management?
Dedicated analytics dashboards | Advanced BI/analytics views | Optional per PO — basic counts required | PARTIAL — basic operational stats exist (tenant dashboard endpoint, Sentinel analytics: real users/tenants/shipments/revenue/KYC counts); no dedicated analytics module | PO: basic counts suffice | — | Analytics page (WORKING, real data) | None if basic counts acceptable | Post-launch | Confirm basic-counts-only is acceptable
AI help assistant | Public Q&A widget | Platform feature | VERIFIED — responds, bounded fallback, no unhandled errors (FIN-10) | Core | — | None | Optional: richer KB | Launch | —
Native mobile app | iOS/Android apps | Roadmap | UNSUPPORTED — responsive web only | PO: reasonable deferral | — | — | None — web works on mobile browsers | Post-launch/roadmap | Confirm deferral
Tenant isolation | Cross-tenant data separation | AGENT.md non-negotiable | VERIFIED — distinct Fleetbase orgs; P21-14 zero cross-tenant records | Core | — | — | None | Launch | —
Admin audit logging | Immutable record of admin actions | AGENT.md audit mandate; PO requirement | PARTIAL — admin_audit_logs records admin.login + runners.listed; CP-proxied mutations (KYC approve, flag toggle, ticket status, tenant/billing actions) write no audit row | Core for supportability | — | Diagnostics audit view exists | Audit middleware on all sentinel write routes | Before launch | —
Feature flags — tenant scope | Per-tenant feature entitlements | Operational control | PARTIAL — global flags work (verified toggle+persist); per-tenant flag endpoint returns CP 404 | Medium | Cannot differentiate tenant features | Feature Flags page (global WORKING) | Implement CP tenant-flag endpoints | Post-launch | Confirm
Sentinel refund/dispute | Payment operations controls | Depends on billing launch | MISSING — honest 404/501, no CP backend | With paid billing | — | Payments page | CP refund/dispute endpoints | With billing launch | —
Runner lifecycle controls | Restart/shutdown runtime runners | Ops tooling | MISSING — honest 501, no CP backend | Low | — | Runners page (list WORKING) | CP runner control endpoints | Post-launch | —
Branded sender domain (@afruheritage.com email) | Customer emails from platform domain | Branding/trust; PO requirement | BLOCKED — provider account rejects @afruheritage.com senders; mail sends as advisory@emidentity.com; SPF strict, no DKIM, DMARC p=none | High for brand trust at public launch | Customers see non-branded sender | — | Provision sender domain + publish DKIM + tighten DMARC (ops action) | Before public pilot | —

## PO Decisions Required
# | Decision | Context | Options
1 | YES — include vendors at launch, or approve deferral? | Vendor registration + marketplace: PARTIAL — FULL backend exists: POST /vendors/register (public, rate-limited), documents, availability, marketplace match, bookings accept/re | PO decision / launch scope
2 | YES — launch with managed drivers only, or require driver portal? | Driver self-service (sign-in, job updates): MISSING — drivers exist only as managed records (Fleetbase proxy); vendor bookings carry driver_name/phone + position tracking, but no drive | PO decision / launch scope
3 | YES — who receives notifications (tenant owner, end customer, both)? | Shipment status notifications: DEFECTIVE — send_shipment_status_update_email + delivered email exist and ARE wired in record_tracking_event (shipment_service.py:948-968), | Fix before launch / launch scope
4 | YES — is central ticket intake required at launch? | Central Afruheritage platform support: MISSING as ticket channel — public tickets require tenant_id (422 without); apex /support honestly explains tenant-routing. Help assistant + | PO decision / launch scope
5 | YES — go-live with paid billing now, or trial-only launch? | Live payment collection (charges): IMPLEMENTED-UNVERIFIED — Paystack + Flutterwave clients exist (initialize/verify, webhooks, authorization_url flow); never exercised end-to- | PO decision / launch scope
6 | YES — is CRM activity UI required at launch? | CRM activity history: PARTIAL — CrmActivity model + GET/POST /customers/{id}/activities endpoints exist; no UI surface for activities | PO decision / launch scope
7 | Confirm deferral | Additional storefront templates (5 demos): PARTIAL — previewable, publish-blocked (fake-content themes now degrade to generic shell) | Post-launch / launch scope
8 | Confirm deferral | Custom domains: PARTIAL — custom_domain_events + domains admin exist; end-to-end custom-domain flow unverified | Post-launch / launch scope
9 | YES — does Afruheritage sell warehouse management? | Warehouse operations: MISSING — no implementation found; not in customer nav | PO decision / launch scope
10 | Confirm basic-counts-only is acceptable | Dedicated analytics dashboards: PARTIAL — basic operational stats exist (tenant dashboard endpoint, Sentinel analytics: real users/tenants/shipments/revenue/KYC counts); no | Post-launch / launch scope
11 | Confirm deferral | Native mobile app: UNSUPPORTED — responsive web only | Post-launch/roadmap / launch scope
12 | Confirm | Feature flags — tenant scope: PARTIAL — global flags work (verified toggle+persist); per-tenant flag endpoint returns CP 404 | Post-launch / launch scope