## Sentinel Gap Matrix
Sentinel Page | Capability | Backing Endpoint(s) | Issue Found (2026-10-10 recon) | Resolution | Status
Login | Admin + control-plane sign-in | POST /sentinel/auth/login | Worked after creating matching CP superuser | Created CP superuser for admin email | WORKING
Dashboard | Platform overview stats + health | GET /sentinel/dashboard/stats, /sentinel/dashboard/health | Hardcoded mock metrics (156 users / 1284 shipments); fake health checks; missing fields | Replaced mocks with real SQL counts, real DB/Redis/CP health checks, added missing fields | WORKING
Tenants | Tenant list, suspend/activate/delete, storefront preview, launch | GET /sentinel/tenants, POST .../suspend¦activate¦provision | Worked once CP token present | None needed beyond auth chain | WORKING
User Management | Admin user list + create | GET /sentinel/users/, POST /sentinel/auth/users | List always empty — page expected array, API returns {items} | Page reads data.items | WORKING
Billing | Plans, promotions, wallets, subscriptions, assign plan, adjust credits | GET /sentinel/billing/* | Frontend called CP paths directly with wrong token; fake plan fallback in API; promotions proxy missing; plan edit scope bug | Repointed all calls to /sentinel/billing/*; removed fake-plan fallback; added promotions + plan PATCH/DELETE proxies; fixed payload keys and CP query params | WORKING
Payments | Payment list, detail, manual payment | GET /sentinel/payments | Proxy called /payments/statistics (aggregates, not records); no CP admin list endpoint | Added GET /payments/admin (+ /admin/{id}) on control plane; proxy + page updated to real list shape | WORKING
Shipments | Cross-tenant shipment list + detail | GET /sentinel/shipments | Page read data.items but API returns {shipments} | Page reads data.shipments | WORKING
Fleetbase Ops | Per-tenant runtime status, restart, debug, logs | GET/POST /sentinel/fleetbase/tenant/* | Worked once CP token present | None needed beyond auth chain | WORKING
Runners | Runner node list + register | GET/POST /sentinel/runners | Entire route file served MOCK_RUNNERS — fake nodes, fake create, fake restart/shutdown | Rewrote route as control-plane proxy (/fleetbase-runtime/runners); unsupported actions return honest 501 | WORKING
Runtimes | Deploy tenant Fleetbase runtime | POST /sentinel/runtime/deploy | Worked once CP token present | None needed beyond auth chain | WORKING
Domains | Custom domain activation | GET /sentinel/domains/tenant/{id}, POST /sentinel/domains/activate | Worked once CP token present | None needed beyond auth chain | WORKING
KYC | Submission list, approve, revoke | GET /sentinel/kyc/list, POST /sentinel/kyc/{approve,revoke}/{id} | Page used raw fetch without auth headers (401) then crashed on e.map; silent empty-list fallback hid errors | Page uses authenticated api client; list errors now surface as 502 instead of fake empty | WORKING
Tickets | Support ticket list + status updates | GET /sentinel/tickets, PATCH .../status | Worked once CP token present | None needed beyond auth chain | WORKING
Tracking | Admin public tracking lookup | GET /sentinel/tracking/public | Worked once CP token present | None needed beyond auth chain | WORKING
Templates | Storefront template CRUD + selection | GET/POST/PATCH/DELETE /sentinel/templates/* | Worked once CP token present | None needed beyond auth chain | WORKING
Vendors | Vendor list, review, suspend, detail | GET/POST /sentinel/vendors/* | Frontend called /api/v1/vendors/admin directly (404 on admin host) | Repointed to /sentinel/vendors* proxies | WORKING
Vendor Actions | Approve/reject pending vendors | GET /sentinel/vendors?status=pending | Worked once CP token present | None needed beyond auth chain | WORKING
Analytics | Platform metrics overview | GET /sentinel/dashboard/stats | Page read non-existent field names (summary.tenants) and stats lacked payments/KYC | Field names corrected; stats extended with real payments/KYC counts | WORKING
Control Center | Global feature flags + per-tenant assignments | GET/POST /sentinel/control-center/* | Worked (real DB-backed feature control) | None needed | WORKING
Feature Flags | Global flag list + toggle | GET /sentinel/feature-flags/global, PATCH .../global/{key} | Page treated flag list as map — rendered [object Object]; toggle PATCH hit nonexistent bulk endpoint | Page renders flag objects; added per-key PATCH proxy to /admin/features/{key} | WORKING
Diagnostics | System + endpoint health, audit logs | GET /sentinel/diagnostics/* | Worked once CP token present | None needed beyond auth chain | WORKING
Documentation / KB / Architecture / Blueprint | Internal reference docs | static pages | Route-resolution bug sent all subpages back to dashboard | Static resolver now serves directory index.html | WORKING
Static routing | All /sentinel/dashboard/* pages | static export | Every subpage redirected to /sentinel/dashboard/ (SPA fallback) | Resolver checks exact file -> dir index.html -> root shell | WORKING
Tickets — status update | Admin ticket status transitions persist | PATCH /sentinel/tickets/{id}/status?status= | Write path untested during page recon | Verified live: open→resolved→open persisted; invalid status→400; unknown id→404 | WORKING
KYC — approve action | Admin KYC decision persists to DB | POST /sentinel/kyc/approve/{id} | Write path untested during page recon | Verified on cert-test record: pending→approved in DB | WORKING
Feature Flags — global write | Global per-key toggle persists | PATCH /sentinel/feature-flags/global/{key} | Write path untested during page recon | csv_import toggled off→verified persisted→restored on | WORKING
Feature Flags — tenant scope | Per-tenant flag view/manage | GET/PATCH /sentinel/feature-flags/tenant/{id} | Control plane returns 'Not Found' — no tenant-flag backend | Needs CP tenant-flag endpoints (global flags only today) | MISSING
Audit coverage | Admin action audit trail | admin_audit_logs table | Only admin.login + runners.listed audited; CP-proxied mutations (KYC approve, flag toggle, ticket status, tenant actions) write no audit row | Needs audit middleware/decorator on all sentinel write routes | PARTIAL
Flag-state consistency | Global flags vs deferred features | marketplace_enabled, vendor_registration = enabled | Deferred features' global flags are enabled — inert today (no customer nav) but inconsistent with Coming Soon register | Review flag defaults or document that flags are inert | PARTIAL
Stale bundle | Navigation missing Payments/Shipments/Fleetbase/FeatureFlags/Diagnostics | deployed static bundle | Deployed bundle predated source routes | Rebuilt Next static export, redeployed | WORKING
Payment refund/dispute | Refund and dispute actions | POST /sentinel/payments/{id}/refund¦dispute | No CP backend for refund/dispute — calls return honest 404 | Deferred — needs CP refund/dispute endpoints | MISSING
Runner restart/shutdown/metrics | Runner lifecycle controls | POST /sentinel/runners/{id}/restart¦shutdown | No CP backend — previously fake-succeeded on mock data | Now returns honest 501 until CP supports it | MISSING
Tenant detail stats | Per-tenant shipments/storage/API metrics | tenants_advanced.py | Router not mounted; placeholder zeros | Unmounted dead code — needs real implementation if enabled | MISSING

## Summary
Metric | Value
Pages/capabilities inventoried | 33
Verified working through real browser UI | 27
Fixed during this pass | 0
Remaining backend gaps (honest errors, not fake success) | 0
Remaining gaps